## Sprint Board
Data-Integrity Sprint — Sid & Rhea · 2 weeks (aggressive) · after the differentiator/Proving-Ground task
Start date: __________ (Day 1 = first Monday after differentiator task signs off). Standup daily 10:00. Status every Friday 4pm.
Day | Week | Task | Tier | Owner | Est (hrs) | Acceptance / done-when | Status
Day 1 | W1 | Setup: venv, run dhs.py + pytest, read dhs.py end-to-end + Build Guide | Onboard | Both | 4 | Both can run the scan + green tests; can explain ColumnProfile & Finding | Not started
Day 1 | W1 | Read v2 Feature-Set doc (Part B) — algorithm for every check | Onboard | Both | 2 | Each can name the 5 new dimensions and pick their checks | Not started
Day 2 | W1 | Tune check_fake_key (only own-key, not foreign keys) | T2 | Sid | 3 | fake_key fires only on supply_id, not shop_id; precision test green | Not started
Day 2 | W1 | Tune check_dirty_categorical (exclude *_id and date cols) | T2 | Rhea | 3 | no dirty_categorical on IDs/dates; still catches text variants | Not started
Day 2 | W1 | Tier-1 quick wins: hidden_structure + mixed_format | T1 | Sid | 3 | both return Findings on seeded/﻿crafted cases; tests green | Not started
Day 3 | W1 | check_validity (range / date / allowed-set rules) | T2 | Sid | 6 | flags impossible dates & out-of-range numerics with samples | Not started
Day 3 | W1 | check_reference_standardization — states (ISO/FIPS) first | T3 | Rhea | 6 | catches shops.state California/CA/Calif → canonical | Not started
Day 4 | W1 | check_cross_field (next_due≥last_exam; consumed≤ordered; status vs date) | T2 | Sid | 6 | surveillance status-vs-date violation flagged; test green | Not started
Day 4 | W1 | check_reference_standardization — defense masks (CAGE/NSN/DoDAAC) | T3 | Rhea | 5 | invalid CAGE/NSN format flagged; valid ones pass | Not started
Day 5 | W1 | Tier-1: locked_table + finish missing_key candidate flag | T1 | Sid | 3 | both implemented; CHECKS list updated | Not started
Day 5 | W1 | check_stale_data (freshness window per partition) | T3 | Rhea | 4 | Fuel Cell 'no rows since March' flagged | Not started
Day 5 | W1 | FRIDAY STATUS #1 — submit weekly report (see template) | Milestone | Both | 1 | Status sent by 4pm Fri using the standard format | Not started
Day 6 | W2 | check_near_duplicate (blocking + fuzzy on roster) | T3 | Rhea | 6 | same person twice (typo) clustered; est dup count reported | Not started
Day 6 | W2 | check_units (mixed kg/lb; precision mismatch) | T3 | Sid | 6 | a seeded unit mix is flagged with evidence | Not started
Day 7 | W2 | check_sensitivity (SSN/DoD-ID/CUI in free-text) | T3 | Sid | 6 | planted SSN-in-notes flagged, value masked | Not started
Day 7 | W2 | check_undocumented_join (MinHash resemblance across tables) | T3 | Rhea | 6 | suggests a real undeclared join; no garbage suggestions | Not started
Day 8 | W2 | Harden check_key_conformity (seed NSN len mismatch; raw vs normalized) | T3 | Sid | 5 | length mismatch flagged; normalized_match≫raw shown | Not started
Day 8 | W2 | Scoring v2 (weight by severity AND % rows touched) | Core | Rhea | 4 | score reflects coverage; HIGH/MED/LOW counts correct | Not started
Day 9 | W2 | Narrative assembler (join related findings into 1 sentence) | Core | Both | 6 | emits the 'your count is wrong because…' sentence | Not started
Day 9 | W2 | Run full scan on EDUCATION dataset (domain-agnostic proof) | Verify | Both | 3 | finds Georgia 3-ways, dup license_id, Carver missing | Not started
Day 10 | W2 | Precision pass + README + final pytest green; demo the scan | Polish | Both | 6 | no obvious false positives; all tests green; 5-min walkthrough | Not started
Day 10 | W2 | FRIDAY STATUS #2 — final report + handoff notes | Milestone | Both | 1 | Status + what's done/left sent by 4pm Fri | Not started
|  | TOTAL planned hours |  |  | 95

## Load by owner
Planned hours by owner
Owner | Hours
Sid | 38
Rhea | 34
Both | 23
Note
'Both' hours are pair/shared. ~6 productive hrs/day assumed; 2 wks ≈ 60 hrs/intern.

## Legend
Legend
Tiers | T1 = profile-only (1–2 hrs) · T2 = value analysis (½–1 day) · T3 = cross-table / reference data (1–2 days)
Owner colors | Sid (blue) · Rhea (purple) · Both (green = pair on it)
Aggressive pace | 2 checks/intern most days. If a T3 slips, cut sensitivity or undocumented_join FIRST; never cut scoring or the Friday status.
Prereq | Starts AFTER the differentiator / Proving-Ground benchmark task is submitted.
Definition of done | green pytest (recall + precision tests) · runs on Education data · narrative sentence · no obvious false positives
Where the work lives | kit/dhs.py (add checks) · kit/test_dhs.py (write test first) · kit/data (seeded answer key)